## 1.Change order Request form
Design Team Procedures - Change Order Request Form 2024 Main Contract Versions - (PWCF1 to PWCF 5)
Project Title |  | [title]
School: |  | [name & location]
Employer’s Representative |  | [Architect]
Quantity Surveyor |  | [QS]
COST SUMMARY
Contract Sum (including VAT) |  | [Contract Sum]
Contract Sum (ex VAT) |  | [Contract Sum ex VAT]
Total value Client/SBS approved Change orders to date |  | 0
Total value of ER’s Authority over full Contract |  | [3 monthly limit x Contract duration/3 ]
MAXIMUM CONSTRUCTION BUDGET [ex VAT] |  | Contract Sum + Approved Change Orders + ER Authority
Total value Change Orders within ER’s Authority to date |  | [cummulative value ex VAT ]
Total Value (ex VAT) unresolved Contractor’s claims |  | [value ex VAT ]
Change Order Approval Request.
No | Description |  | Date | Nett Extra
| [The reason for each change order shall be fully explained and justified with comment from the relevant Design Team member appended as appropriate] ( See atatched Tabs) |  | [date] | Value (ex VAT)
Previous approved Change Orders above €2,000 (or otherwise requiring approval) within last 3 months.
No | Approved Change Orders within last 3 months |  | Date Approved | Value (ex VAT)
[1-x] | Cumulative Cost of approved Change orders (older than 3 months) |  | n/a | [cumulative value]
x+1 | [Summary Description including reason for change]
x+2 | [Summary Description including reason for change]
[Add lines as required]
[1-xx] | Cumulative cost of approved Change orders from start of Project to current date |  | n/a | 0
I confirm that no Change Orders have been authorised outside the limits of my authority not approved by both the Client and the School Building Section. I further confirm that no change order has been issued which will have the effect of causing or contributing to a reduction in safety, scope, quality or usefulness of the Works without the Employer’s approval, whether within the financial limits of my authority or not
Signed : |  |  | Date:
Firm |  |  | [Employer’s Representative]

## 2.Summary & Details
Design Team Procedures - Change Order Request Form 2024 - Main Contract Versions - (PWCF1 to PWCF 5)
Claim Description / Title:
Cl 9.3/10.3 Claim / Change Order No:
Date Change Order Request Form Submitted:
10.3 Claim Notification Process & Dates
Date When Initial 10.3 Notification Submitted:
Dates when detailed calc and final substantiation submitted:
Date when additional information request made by ER:
Date when addition information request was responded to:
Date When Determination was due to be issued under the Contract:
Status of these claimed Works on Site
Adjustment to Contract Sum Claimed by Contractor: |  |  | Adjustment to Programme Duration Claimed
Delay (Value) | 0 |  | Duration of Delay Claimed |  |  |  | Day(s)
Works (Works value) | 0
Total Value of Claim Submitted | 0
The Design Team must state where the Change Order arises from: |  | X (mark)
A Client Requested change |  |  | Tendered Daily Delay Rate: |  |  |  | €/day
A Contractor claim (A solely Contractor generated item with no change to WR) |  |  | Number of Contract Threshold Days T1 |  |  |  | Day(s)
An employer claim (a credit) |  |  | Number of Contract Threshold Days T2 |  |  |  | Day(s)
Unforeseeable circumstances (An Unknown Requirement) |  |  | Balance of Threshold days currently remaining (T1) |  |  |  | Day(s)
A Design Team omission (A Design Team required change to WR) |  |  | Balance of Threshold days currently remaining (T2) |  |  |  | Day(s)
The inadequacy of the Works Requirements (DT required change to WR)
WR = Works Requirments
Summary / Description / Justification of claim
Design Team Discipline Claim Relates to:
See tab 4 with requirement for relevant DT member to provide comment in relation to this claim in addition to the above information
Contractual Entitlement: (Schedule 1K) (Detail and description of schedule 1K event which applies to this Claim) (Drop Down Menu)
Additional Schedule 1K events if Applicable
Is the Schedule K Event which applies | Yes / No
A Compensation Event
A Delay Event
Comments From ER on claim and explanation as to why this claim is been deemed Valid or Invalid
ER recommended status of claim as submitted | X (mark)
Valid Claim
Invalid Claim
Approach to assessment and valuation of detailed calculation (Works) (more than one can be selected) : |  |  |  | X (mark)
Adjustment valued in accordance with CL 10.6.1
Adjustment valued in accordance with CL 10.6.2
Adjustment valued in accordance with CL 10.6.3
Adjustment valued in accordance with CL 10.6.4
Explanation of Valuation Approach as Selected above under CL 10.6 (More than one valuation of claim approach may apply)
Confirmation that Pricing Document Rates Unadjusted have been used in relation to where the below valuation approaches apply | [5 empty] | Yes / No / N/A
Adjustment valued in accordance with CL 10.6.1
Adjustment valued in accordance with CL 10.6.2
Approach to detailed calculation (Delays): (Drop down options Yes, No, N/A)
The Delay Costs have been valued in accordance with the daily rate of delay cost tendered by the Contractor in the Schedule, part 2D
Total number of days awarded for adjustment to the contract programme (this claim) |  |  |  |  | Days
Number of T1 Days proposed to be used as part of this proposed determination |  |  |  |  | Days
Number of T2 Days proposed to be used as part of this proposed determination |  |  |  |  | Days
Total number of days to be awarded at the tendered daily delay rate (as part of this claim) (EOT) |  |  |  |  | Days
The date for Substantial Completion can only adjusted by Delay Events listed in the Schedule Part 1K
Current Employer ER/DTQS assessment (Works Costs) |  | 0
Current Employer ER/DTQS assessment (Delay Costs) |  | 0
Total value of additional funding recommended / requested |  | 0
Attachments (Mandatory)
1. Standard DOE Change order request form (Cover)
2. Summary and Details Form
3. DTQS Assessment
4. Comment from relevant design team member to be appended to Change Order Request Form
5. Supporting information / Photographs / Mark-ups / Drawings

## 3.DTQS Assessment
Design Team Procedures - Change Order Request Form 2024 - Main Contract Versions - (PWCF1 to PWCF 5)
3. Commercial Assessment of Claim Submitted (Can be in Preferred DTQS Format with relevant comparable information)
Project Name: |  |  | Claim Description / Title: | [7 empty] | Contractor Claim Reference No:
|  | Contractor Submission |  |  |  | DTQS - Assessment
Ref | Description | Qty | Unit | Rate | Total | Qty | Unit | Rate | Total | Diff | Notes/Comments
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 | 0
| Total Excl VAT | Contractor Submission Total: 0; DTQS - Assessment Total: 0; DTQS - Assessment Diff: 0
Notes, Comments, Qualifications and Exclusions:
(a)
(b)
(c)
****** Can be in Preferred DTQS Format with relevant comparable information

## 4. Comments from Relevant DT
Design Team Procedures - Change Order Request Form 2024 - Main Contract Versions - (PWCF1 to PWCF 5)
4.Comments from relevant Design Team Member in relation to this claim
Claim Description / Title:
Design Team discipline claim relates to:
Comments from relevant Design Team Member:

## 5.Supporting Information
Design Team Procedures - Change Order Request Form 2024 - Main Contract Versions - (PWCF1 to PWCF 5)
5.Supporting information / Photographs / Mark-ups / Drawings
Claim Description / Title:
Photographs / Drawing Mark Ups

## Schedule 1K
K Delay Events, Compensation Events, Programme Contingency, Delay Costs, Adjustments
(Sub-Clauses 9.3,9.4,10.1,10.6,10.7, clause 14
Schedule1K | EVENT | Delay Event | Compensation Event
1 | Tender Schedule 1K1 - The Employers' Representative gives the Contractor a Change Order | Yes | Yes
2 | Tender Schedule 1K2 - The Employer’s Representative directs the Contractor to search for Defects or their cause and no Defect is found, and the search was not required because of a failure of the Contractor to comply with the Contract | Yes | Yes
3 | Tender Schedule 1K3 - The Employer’s Representative directs the Contractor to suspend work under sub-clause 9.2 | Yes | Yes
4 | Tender Schedule 1K4 - The Contractor suspends work in accordance with sub-clause 12.3 | Yes | Yes
5 | Tender Schedule 1K5 - There is a factual error in information about the Site or setting out information in the Works Requirements. [This does not include an error of interpretation.] | Yes | Yes
6 | Tender Schedule 1K6 - The Employer takes over part of the Works before Substantial Completion of the Works and any relevant Section | Yes | Yes
7 | Tender Schedule 1K7 - The Employer’s Representative does not give the Contractor an instruction required under sub-clause 4.5.4 within the time required under sub-clause 4.11.2 when the Contractor has asked for the instruction in accordance with sub-clause 4.11.1 | Yes | Yes
8 | Tender Schedule 1K8 - The Employer does not allow the Contractor to occupy and use a part of the Site in accordance with sub-clause 7.1 | Yes | Yes
9 | Tender Schedule 1K9 - The Employer does not give the Contractor a Works Item or other thing as required by the Contract when the Contractor has asked for it in accordance with sub-clause 4.11.1 | Yes | Yes
10 | Tender Schedule 1K10 - Employer’s Personnel working on the Site under clause 7.6 interfere with the execution of the Works on the Site, and the interference is unforeseeable and not in accordance with the Contract | Yes | Yes
11 | Tender Schedule 1K11 - The Employer instructs the Contractor under sub-clause 3.2.3 to rectify loss of or damage to Risk Items for which the Contractor is not responsible | Yes | Yes
12 | Tender Schedule 1K12 - Loss of or damage to the Works that is at the Contractor’s risk in accordance with sub-clause 3.2 | Yes | No
13 | Tender Schedule 1K13 - A weather event as described below | Yes | No
14 | Tender Schedule 1K14 - A strike or lockout affecting the construction industry generally or a significant part of it, and not confined to employees of the 1Contractor or any Contractor’s Personnel | Yes | No
15 | Tender Schedule 1K15 - Delay to the Works caused by the order or other act of a court or other public authority exercising authority under Law, that did not arise as a result of or in connection with an act, omission or breach of Legal Requirements of the Contractor or the Contractor’s Personnel or a breach of the Contract by the Contractor | Yes | No
16 | Tender Schedule 1K16 - A breach by the Employer of the Contract delaying the Works that is not listed elsewhere in this table. | Yes | Yes
17 | Tender Schedule 1K17 - A difference between the Contract value of the Works according to the quantities and descriptions in the Pricing Document and the Contract value of the Works described in the Works Requirements, because the Pricing Document, when compared with the Works Requirements  includes an incorrect quantity or  includes an item that that is not included in the Works Requirements or  excludes an item that is included in the Works Requirements or  gives an incorrect item description and the difference for an item in, or that should have been in, the Pricing Document is more than €500 | No | Yes
18 | Tender Schedule 1K18 - An item of Archaeological interest or human remains is found on the Site, and it was unforeseeable | Yes | Yes | ***
19 | Tender Schedule 1K19 - The Contractor encounters on the Site unforeseeable ground conditions (not resulting from weather) or unforeseeable human-made obstructions in the ground, other than Utilities | Yes | Yes | ***
20 | Tender Schedule 1K20 - The Contractor encounters unforeseeable Utilities in the ground on site | Yes | Yes | ***
21 | Tender Schedule 1K21 - Owners of Utilities on the Site do not relocate or disconnect Utilities as stated in the Works Requirements, when the Contractor has complied with their procedures and the procedures in the Contract, and the failure is unforeseeable | Yes | Yes | ***
**** - Optional Schedule 1K Events (Compensation)
Utilities means conducting media and apparatus for water, sewage, electricity, gas, oil, telecommunications, data, steam, air, or other services, and associated apparatus and structures.
A condition, circumstance or occurrence is unforeseeable if an experienced contractor tendering for the Works could not have reasonably foreseen it on the Designated Date, having inspected the Site and its surroundings and having satisfied itself, insofar as practicable and taking into account any information in connection with the Site provided by the Employer, as to all matters concerning the Site, including its form and nature and its geotechnical, hydrological and climatic conditions.
WE 1.0 is the document entitled Weather Events WE 1.0 published on www.constructionprocurement.gov.ie on the Designated Date.
A weather measurement for a month means each of the following:
a | the number of days with rainfall exceeding 10 millimetres
b | the number of days with minimum air temperature less than 0 degrees Celsius and
c | the number of days with maximum mean 10 minute wind speed exceeding 15 metres per second as recorded at weather station.
If no weather station is named, the Met Éireann station nearest the Site is used. If the station named, or the nearest one, does not record the weather measurements, the station nearest the Site that records that weather measurement is used
A weather event is when in a month between the Starting Date and the Date for Substantial Completion of the Works a weather measurement exceeds the number of days for the same item, the same weather station, and the corresponding month in WE 1.0
If a weather event occurs in a month and there is to be an extension to a Date for Substantial Completion under sub-clause 9.3.2, the amount of the extension is the lesser of (a) the extension to be made under sub-clause 9.3.2 and (b) the difference between the weather measurement and the number of days for the corresponding item in WE1.0. No day is counted for more than one weather measurement.
*******************Please refer to the specific Contract Tender Schedule for allocation of Schedule K Delay and Compensation Events****************